## Tabelle1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2023-09-30
Group Number
Participant 1 |  | Deyaa Yousef , if21b021
Participant 2
Participant 3
Participant 4
Participant 5
Mentor |  | Harald Wahl
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Researching | 6 | 10 | 4
2 | Enviroment Setup VS Code ,installing Packages | 1 | 1 | 0
3 | Created initial HTML structure for the main page. | 1 | 0.5 | -0.5
4 | Design the layout for input fields, buttons, and result display. | 1 | 2 | 1
5 | had to reasearch again about factors of living quality | 3 | 5 | 2
6 | Develop a component to take user input for the address. | 1 | 1 | 0 |  |  | i wasn't finished with it yet
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 6.5 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol