## Tabelle1
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2023-10-09
Group Number
Participant 1 |  | Deyaa Yousef , if21b021
Participant 2
Participant 3
Participant 4
Participant 5
Mentor |  | Harald Wahl
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Implement validation for address input. | 2 | 2.5 | 0.5
2 | Reseaching again about Calculating living Quality | 3 | 4 | 1 |  |  | i tried a lot of formels on paper to caluclate living quality using some of factors
3 | Create a component to display the living standard result. | 2 | 2 | 0
4 | Style the result to be visually appealing and easy to understand. | 1 | 0.5 | -0.5
5 | Set up a Node.js server using Express. | 2 | 1900-01-02 | 1
6 | Meeting with mr Wahl disscussed how coukd i use the factors from open Data Wien to create formel | 1 | 1 | 0
7 |  |  |  | 0
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 2 | 0 | 0
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol