## Tabelle1
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2023-10-16
Group Number
Participant 1 |  | Deyaa Yousef , if21b021
Participant 2
Participant 3
Participant 4
Participant 5
Mentor |  | Harald Wahl
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Define API endpoint to handle requests | 2 | 4 | 2 | 1
2 | Reseaching again about Calculating living Quality | 3 | 5 | 2 | 1
3 | Integration with Wien - Open Data | 3 | 6 | 3 |  | 1
4 | Develop logic to fetch and process data based on the provided address. | 1 | 0.5 | -0.5 | 1
5 | Create the algorithm to calculate the living standard based on the fetched data. | 3 | 1900-01-06 | 4 | 1 |  | i tried a lot of formels on paper to caluclate living quality using some of factors
6 | Creating functions to extract the specific Properties from the files of factors like Address,Name,Coordinates | 3 | 5 | 2
7 | exchange the user's Address into coordinates using mapquest api services | 2 | 1.5 | -0.5
… | Developed a function using haversine fromel to get the distance betwenn 2 points | 2 | 3 | 1
… | displaying the Nearby Addresses to the given useer address | 2 | 2 | 0
n |  |  |  | 0
7 |  |  |  | 13 | 4 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol