## Tabelle1
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2023-10-22
Group Number
Participant 1 |  | Deyaa Yousef , if21b021
Participant 2
Participant 3
Participant 4
Participant 5
Mentor |  | Harald Wahl
List the Ids of the Requirements which are subject to the review
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
1 | Create the algorithm to calculate the living standard based on the fetched data | 2 | 5 | 3 | 1
2 | Reseaching again about Calculating living Quality | 2 | 2 | 0 | 1
3 | Integration with Wien - Open Data | 3 | 3 | 0 | 1
4 | Develop logic to fetch and process data based on the provided address. | 2 | 1 | -1 | 1
5 | Create the algorithm to calculate the living standard based on the fetched data. | 3 | 1900-01-02 | 0 | 1
6 | Implement error handling for incorrect address input or any other potential errors. | 2 | 3 | 1 |  | 1
7 | finishing Documentation | 2 | 4 | 2
… |  |  |  | 0
… |  |  |  | 0
n |  |  |  | 0
7 |  |  |  | 5 | 5 | 1
fill out the orange fields
Transfer your estimate as well as your real effort from your planing tool to this protocol